## Book_Project_Plan_Template
Clear Sight Books - Book Project Plan Template
Phase/Task | Assigned To | Start Date | Due Date | Completed Date | Priority | Status | Notes
Project Setup
Set up process/folders (paper, computer, email) | Author/Project Manager | [5 empty] | Decide how you are going to work.
Review project plan and marketing plan/timing | Author/Project Manager
Identify team | Author/Project Manager
Strategic Positioning
Define primary goal--sell books, get clients, legacy? | Author/Project Manager | [5 empty] | Make sure your goal is clear; that drives tactics and decisions.
Define audience--who is your ideal reader? | Author/Project Manager
Get comps for use in cover design and strategic positioning | Author/Project Manager
Draft title and subtitle | Author/Project Manager | [5 empty] | The earlier you land on the title, the better. However, sometimes you don't know the title until you are done writing.
Draft book description | Author/Project Manager
Draft author bio | Author/Project Manager
Get endorsements | Author/Project Manager
Develop metadata (categories, keywords, etc.) | Author/Project Manager
Capture important info in a strategic brief (or "book proposal") | Author/Project Manager
Review and finalize all elements holistically before going to production | Author/Project Manager
Writing and Revision | [6 empty] | Write your book! This phase might happen before you think about the full publishing project. (No point in developing a production plan without a manuscript…) I usually come in at the revision stage, which is why I include it.
Introduction | Author/Editor
Ch 1 | Author/Editor
Ch 2 | Author/Editor
Ch 3 | Author/Editor
Ch 4 | Author/Editor
Ch 5 | Author/Editor
Ch 6 | Author/Editor
Ch 7 | Author/Editor
Ch 8 | Author/Editor
Conclusion | Author/Editor
Holistic read for consistency and flow | Author/Editor
Get critique or feedback from editors as needed (developmental, content, etc.) | Author | [5 empty] | This is optional but useful; be sure to account for the time in your planning.
Final edits | Author/Editor
Review by subject-matter experts (SMEs) or beta readers as needed | Author | [5 empty] | Allow 2-3 weeks for this. Plan ahead.
Copyediting
Introduction | Editor | [5 empty] | Get a fresh set of eyes for copyediting.
Ch 1 | Editor
Ch 2 | Editor
Ch 3 | Editor
Ch 4 | Editor
Ch 5 | Editor
Ch 6 | Editor
Ch 7 | Editor
Ch 8 | Editor
Conclusion | Editor
Production Logistics
Set up accounts as needed (KDP, IS, D2D, Bowker, etc.) | Author/Project Manager
Determine pricing and whether to include price on cover | Author/Project Manager | [5 empty] | Need to do this before finalizing the cover.
Confirm title and subtitle | Author/Project Manager | [5 empty] | Need to do this before assigning ISBN.
Finalize book description and bio | Author/Project Manager | [5 empty] | Need to do this before finalizing the cover.
Assign ISBN | Author/Project Manager | [5 empty] | Need to do this before finalizing the cover.
Get LCCN | Author/Project Manager | [5 empty] | This must be requested before publication.
Register with Copyright Office | Author/Project Manager | [5 empty] | This can be done right before or right after publication; if before, you can upload the book PDF.
Check front matter and back matter for completeness | Author/Project Manager
Design and Formatting
Design conversation with author/designer | Author/Designer | [5 empty] | Design and Production Logistics usually overlap; some things you need before design, some after.
Develop creative brief--cover comps, design input from author | Designer/Project Manager
Get author photo | Author
Round 1 cover options | Designer
Round 2 cover options | Designer
Decision from author | Author
Paperback full cover | Designer
Hardback full cover | Designer
Round 1 interior design | Designer | [5 empty] | Do interior design after cover design to ensure it is complementary.
Round 2 interior design | Designer
Design signoff by author | Author
Formatting of interior | Designer/Formatter
Determine paper color (white, cream), cover finish (matte, glossy) | Author | [5 empty] | Paper color affects spine width.
Get final cover templates with correct spine width and ISBNs for designer | Author/Project Manager | [5 empty] | May need templates for KDP, IS, and any other POD platforms.
Finalize covers | Designer
Proofreading
Proof formatted interior | Proofreader | [5 empty] | Get another fresh set of eyes for proofreading.
Review any critical changes | Author
Make final changes to interior | Designer/Formatter
Proof paperback cover | Proofreader
Proof hardback cover | Proofreader
Final cover corrections | Designer
KDP Paperback | [6 empty] | I always do this first because it is fastest to get a print proof.
Upload first draft files to KDP for paperback | Author/Project Manager
Order print proofs from KDP | Author/Project Manager | [5 empty] | KDP paperback proofs usually arrive quickly (a few days).
Review KDP print proofs and make corrections to cover and interior as needed | Author/Project Manager/Designer
Make changes to interior as needed | Designer/Formatter
Upload second set of files to KDP | Author/Project Manager
Approve on KDP (or schedule release date) | Author/Project Manager
KDP hardback (if applicable)
Upload files to KDP | Author/Project Manager
Order proof copy | Author/Project Manager
Review for correctness and color | Author/Project Manager/Designer
Uploaded corrected files if needed | Author/Project Manager
Approve for publication | Author/Project Manager
IngramSpark Paperback
Upload files to IngramSpark | Author/Project Manager | [5 empty] | The approval process for uploaded files can take several days.
Order proof | Author/Project Manager | [5 empty] | IS proofs usually take 2-3 weeks, especially for hardbacks, so allow plenty of time.
Review proofs | Author/Project Manager/Designer
Upload second set if needed | Author/Project Manager
Approve for publication | Author/Project Manager
IngramSpark Hardback
Upload to IngramSpark | Author/Project Manager
Order IngramSpark proofs | Author/Project Manager
Review IngramSpark proofs | Author/Project Manager/Designer
Upload second set of files if needed | Author/Project Manager
Approve for publication | Author/Project Manager
Ebook Production
Format for e-reader (Word doc, EPUB, etc.) | Author/Formatter | [5 empty] | I wait to start this until I have finished proofing the first print copy to make sure it is truly done.
Test on Kindle Previewer (desktop) and on D2D EPUB tester and Calibre as needed | Author/Formatter
Upload to KDP and preview | Author/Formatter/Project Manager
Upload to D2D, Apple, IS, etc. as needed | Author/Formatter/Project Manager
Approve for publication (set release date) | Author/Project Manager
Test live ebook day after publication | Author/Project Manager
Verify ebook and both print books get matched on Amazon | Author/Project Manager
Audiobook
Determine if doing audiobook | Author
Edit/revise based on listening to the book (only if needed; try to avoid) | Author/Editor
Create supplemental material as needed (e.g., tables, diagrams) | Author
Create pronunciation guide for the narrator | Author
Find narrator | Author/Project Manager
Record and produce the audiobook | Narrator
Assign ISBN | Author/Project Manager
Determine pricing | Author/Project Manager | [5 empty] | The platform may not let you decide the price, or it may suggest pricing when you upload your files.
Upload files to platforms (ACX, Findaway, etc.) | Author/Project Manager | [5 empty] | It can take several weeks before your audiobook becomes available for sale.
Marketing
Create a package for requesting endorsements | Author/Project Manager | [5 empty] | If you are asking for endorsements, allow 4-8 weeks. Make this request with the copyedited manuscript or with the initial formatted interior.
Endorsements - edit and finalize those received | Author/Project Manager | [5 empty] | If these are going in the book or on the cover, be sure to get them to the designer early.
Develop marketing plan based on goals: both launch plan and ongoing plan | Author/Project Manager
Create/update author/business website | Author/Project Manager
Set up Author Central (or update profile with new book) | Author/Project Manager
Set up books on Goodreads | Author/Project Manager | [5 empty] | These sometimes populate automatically from Amazon.
Order books for launch events | Author/Project Manager | [5 empty] | Allow 3-4 weeks; you cannot order KDP books until they are live; you can order IS books before the publication date.
Postproduction
Send book to Library of Congress | Author/Project Manager | [5 empty] | This is a requirement if you got an LCCN.
Register with Copyright Office | Author/Project Manager | [5 empty] | You can also do this before you go live with the book.
Send book to Copyright Office | Author/Project Manager | [5 empty] | If you register before production, you can upload the PDF.
Update Bowker if needed (e.g., add cover, update description) | Author/Project Manager
Create project documentation | Author/Project Manager | [5 empty] | Document what you did, so you can remember it for next time!
Clean up Dropbox, hard drive, etc. | Author/Project Manager
Send thank-you copies out to reviewers, team members | Author/Project Manager